## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2225-swen-261-04-e-deal
Get a Single Product | When I click on a product's button, I will see information about that product. | Pass
Delete a Single Product | What I click the delete product button, I can delete a product. | Pass
Update a Single Product | What I click the update product button, I can edit the information about a product. | Pass
Search for Products | What I click the search button and enter text, I will see the products that match that search. | Pass
Get Entire Inventory | When I click the all products button, I will see all the products in the inventory. | Pass
Create New Product | When I click the add product button I can add a product to the inventory | Pass
User Login | When I enter my username I will be logged in to my account | Pass
Create User Account | If I enter a username that is does not have an account, a new account will be created. | Pass
Login to Admin Account | When I login with my admin username I will enter the admin view and can edit the inventory. | Pass

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to be able to add items to my cart so I can view them later. | Given there is an available item to buy, when I add it to the cart, then the inventory and my cart will update. | Pass |  | Pass | EL 4/9/23
| Given an item is out of stock, when I add it to the cart, it will notify that there's none available | Pass |  | Pass | EL 4/9/23
As an admin I want to be able to login so that I can edit the inventory | Given I login with my admin username I will enter the admin view and can edit the inventory. | Pass |  | Pass | EL 4/9/23
As a user I want to be able to create an account | Given I click the create account button and enter a username, a new account will be created. | Pass |  | Pass | EL 4/9/23
As a user I want to be able to login into the application | Given I enter my username I will be logged in to my account | Pass |  | Pass | EL 4/9/23
As a user I want to be able to create an account | Given I click the create account button and enter a username, a new account will be created. | Pass |  | Pass | EL 4/9/23
As a user I want to be able to login into the application | Given I enter my username I will be logged in to my account | Pass |  | Pass | EL 4/9/23
As a buyer I want to be able to view my shopping so that I can see what items I have saved for checkout. | Given that I am on the homepage when I press the shopping cart icon then I expect the webpage to take me to my shopping cart | Pass |  | Pass | EL 4/9/23
As a Buyer, I want to be able to remove items from my cart so that I can choose how much of an item I want to buy | Given that there is at least one item in my cart, when I press the remove button then the selected item should be removed from my cart | Pass |  | Pass | EL 4/9/23
| Given that there are no items in my cart, when I look into my chopping cart then there should be no option to remove | Pass |  | Pass | EL 4/9/23
| Given that there is at least one item in my cart, when I press the add button it should increase the number of that item in my cart | Pass |  | Pass | EL 4/9/23
| Given that there is at least one item in my cart, when I press the remove button it should decrease the number of that item in my cart. When there is only one of that item there should be no option to further reduce that number | Pass |  | Pass | EL 4/9/23
As a Buyer I want to be able to checkout so that I can receive the item I wish to buy | Given that I click the checkout button, the page will navigate to the checkout page. |  |  | Pass | DG 4/9/23
| Given that I am on the checkout page, I will see a list of products that are in my shopping cart and the total price of all the items. |  |  | Pass | DG 4/9/23
| When I click the purchase button, my shopping cart will be cleared. |  |  | Pass | DG 4/9/23
As a user I want the store page to look nice so that I am likely to use the store. | Given that I log into the website, then it should be easily navigatable |  |  | Pass | AL 4/9/23
As a user I want the shopping cart page to look nice so that I am likely to use the store. | Given I view the shopping cart page, it looks nice and is well organized. |  |  | Pass | AL 4/9/23
As a user I want the login page to look nice so that I am likely to use the store. | Given I open up the webpage the login should look trust worthy |  |  | Pass | AL 4/9/23
As a user I want to be able to add reviews | Given that I enter text for a review and click the add review button then my review will be added to the product. |  |  | Pass | DG 4/9/23
As a user I want to be able to view all the reviews left on a product. | Given that I am on the store page then I will see all the reviews for each product. |  |  | Pass | DG 4/9/23